## Sheet1
M&E DEVELOPMENT CONTROL SHEET as 16 January, 2022
SN | PENDING ISSUE | MHUSIKA | REMARKS
1 | Maandalizi ya Ratiba za UAT, Data Entry, Training & RollOUT | LILIAN NGOWI
2 | Maandalizi ya Test Cases | AMENJIEKA KISANGA | DONE
3 | badge bell notification | maro
4 | User custom password change | shaaban | DONE!
5 | Forgotten password updates refine | shaaban/maro | DONE! waiting front consumer.
6 | authentication JWT | shaaban | DONE!
7 | profession seeding | shaaban/victor
8 | dublicate validation (activity progresses) + funddisbursement + milstones if exist | victor/maro | DONE !
9 | action function: (DELETE, UPDATE) | dismas
10 | Kuongeza project kwenye objectives | victor/maro
11 | System Wording/Spelling/Grammer | wote
12 | Default institution and permission(asione taasisi au role zisizomuhusu)== FILTERS | victor/dismas | DONE! waiting front consumer.
13 | Uploading GFS codes CSV/ also on other arears | shaaban/Dismas | DONE!
14 | printing, exporting pdf, | Dismas
15 | funddisbursement control | maro | DONE
16 | PDF/image previewer | Maro | DONE
17 | uploading files to server | shaaban | Waiting eGA security abandonment on servers for TAWA hunting Auction!
18 | menu kuu ya moduli za wajibika | wote
19 | Directory Arrangement(Frontend/Backend) | Shaaban/Maro. | Waiting eGA security abandonment on servers for TAWA hunting Auction!
20 | Renaming System Title to e-M & E for MNRT
21 | Merging Institutions reports
22 | Weekly report notifications(sms & email)
23 | Admin to reverse approved activity progress
24 | Report filtering